## Sheet1
Pizza Delivered Quickly Factory Locator Subsystem (Waterfall Development)
| # Units/Hrs | Cost/Unit/Hr. | Subtotals | WBS Level 2 Totals | % of Total
WBS Items
1. Requirements |  |  |  | 636 | 5.185%
Gathering Requirements | 72 | 4 | 288
Document Preparation | 240 | 1.3 | 312
Document Revision | 72 | 0.5 | 36
2. Design |  |  |  | 2251.2 | 18.35%
Wireframe Preparation | 48 | 5 | 240
Markup Generation | 240 | 7 | 1680
Design Finilization (Finishing Touches) | 72 | 4.6 | 331.2
3. Implementation |  |  |  | 6610.8 | 53.9%
IPO Chart Creation | 12 | 0.7 | 8.4
Identification of Units | 48 | 3.5 | 168
Allocate Units to Teams | 24 | 0.3 | 7.2
Development of Units | 480 | 9.6 | 4608
Unit Coupling and Testing | 192 | 6.7 | 1286.4
Unit implementation to Markup (Prototype Creation) | 72 | 7.4 | 532.8
4. Verification |  |  |  | 916.8 | 7.475%
Integration Testing | 168 | 4.3 | 722.4
Requirements Checklisting | 72 | 2.7 | 194.4
5. Maintenance |  |  |  | 1850.4 | 15.09%
System Testing | 240 | 7.5 | 1800
Requirement Identification | 24 | 2.1 | 50.4
TOTAL |  |  |  | 12265.2