## Sheet1
Pizza Delivered Quickly Factory Locator Subsystem (Waterfall Development)
| # Units/Hrs | Cost/Unit/Hr. | Subtotals | WBS Level 2 Totals | % of Total
WBS Items
1. Requirements |  |  |  | 31200 | 6.95%
Gathering Requirements | 72 | 75 | 5400
Document Preparation | 240 | 100 | 24000
Document Revision | 72 | 25 | 1800
2. Design |  |  |  | 37440 | 8.34%
Wireframe Preparation | 48 | 60 | 2880
Markup Generation | 240 | 120 | 28800
Design Finilization (Finishing Touches) | 72 | 80 | 5760
3. Implementation |  |  |  | 309720 | 68.99%
IPO Chart Creation | 12 | 20 | 240
Identification of Units | 48 | 10 | 480
Allocate Units to Teams | 24 | 50 | 1200
Development of Units | 480 | 440 | 211200
Unit Coupling and Testing | 192 | 370 | 71040
Unit implementation to Markup (Prototype Creation) | 72 | 355 | 25560
4. Verification |  |  |  | 40800 | 9.088%
Integration Testing | 168 | 200 | 33600
Requirements Checklisting | 72 | 100 | 7200
5. Maintenance |  |  |  | 29760 | 6.629%
System Testing | 240 | 120 | 28800
Requirement Identification | 24 | 40 | 960
TOTAL |  |  |  | 448920