## Sheet1
Pizza Delivered Quickly Factory Locator Subsystem (Waterfall Development)
| 1 | 2 | Total
WBS Items
1. Requirements
Gathering Requirements | 30 |  | 30
Document Preparation | 10 |  | 10
Document Revision | 15 |  | 15
2. Design |  |  | 0
Wireframe Preparation | 150 |  | 150
Markup Generation | 240 |  | 240
Design Finilization (Finishing Touches) | 30 |  | 30
3. Implementation |  |  | 0
IPO Chart Creation | 5 |  | 5
Identification of Units | 10 |  | 10
Allocate Units to Teams | 14 |  | 14
Development of Units | 300 | 300 | 600
Unit Coupling and Testing |  | 240 | 240
Unit implementation to Markup (Prototype Creation) |  | 140 | 140
4. Verification |  |  | 0
Integration Testing |  | 70 | 70
Requirements Checklisting |  | 10 | 10
5. Maintenance |  |  | 0
System Testing |  | 60 | 60
Requirement Identification |  | 0 | 0
1624