## Sheet1
Pizza Delivered Quickly Factory Locator Subsystem (Waterfall Development)
| 1 | 2 | Total
WBS Items
1. Requirements
Gathering Requirements | 288 |  | 288
Document Preparation | 312 |  | 312
Document Revision | 36 |  | 36
2. Design |  |  | 0
Wireframe Preparation | 240 |  | 240
Markup Generation | 1680 |  | 1680
Design Finilization (Finishing Touches) | 331.2 |  | 331.2
3. Implementation |  |  | 0
IPO Chart Creation | 8.4 |  | 8.4
Identification of Units | 168 |  | 168
Allocate Units to Teams | 7.2 |  | 7.2
Development of Units | 2304 | 2304 | 4608
Unit Coupling and Testing |  | 1286.4 | 1286.4
Unit implementation to Markup (Prototype Creation) |  | 532.8 | 532.8
4. Verification |  |  | 0
Integration Testing |  | 722.4 | 722.4
Requirements Checklisting |  | 194.4 | 194.4
5. Maintenance |  |  | 0
System Testing |  | 1800 | 1800
Requirement Identification |  | 50.4 | 50.4
12265.2