## Sheet1
Cost Estimate
WBS Categories | # Units/Hrs | Cost/Unit/Hr. | Subtotals | WBS Level 2 Totals | % of Total
1.1 Project management |  |  |  | 60000 | 55.96%
1.1.2 Project manager | 960 | 20 | 19200
1.1.2 Project team | 960 | 20 | 19200
1.1.3 IT guy | 720 | 30 | 21600
1.2 Hardware( 3 laptops and internet access for Kim, Ashok, and Alfreda) |  |  | 10000 | 10000 | 9.327%
1.3 Software |  |  |  | 2480 | 2.313%
1.3.1 Outsourcing
1.3.1.1 Domain name and site hosting |  |  | 500
1.3.1.2 Donation acceptance feature of website |  |  | 30
1.3.1.3 Video creation for website |  |  | 200
1.3.2 In-house Development |  |  | 0
1.3.2.1 Guidelines and templates for events |  |  | 100
1.3.2.2 Acceptance of ideas for needed new products or services |  |  | 50
1.3.2.3 Custom site for 20 events | 20 | 30 | 600
1.3.3 Testing |  |  | 1000
1.4 Business Plan |  |  |  | 380 | 0.3544%
1.4.1 Internal labor | 20 | 12 | 240
1.4.2 Legal information/assistance | 10 | 14 | 140
1.5 Travel |  |  | 30000 | 30000 | 27.98%
1.6 Events |  |  |  | 4350 | 4.057%
1.6.1 Internal labor | 20 | 10 | 200
1.6.2 Consultant labor | 10 | 15 | 150
1.6.3 Refreshments | 4 | 800 | 3200
1.6.4 Prizes | 4 | 200 | 800
Total |  |  | 107210
Assumptions
project management team works for 40 hours each week
IT guy works for 30 hours each week
project team works for 40 hours